## dummy
Software Component	Version in Dockerfile	Dockerfile source reference (downloaded, rockyLinuxRepo)	Version in Debian 12 Repositories	Debian Repo (main, contrib, non-free,...)	Update changes	Notes & Hints
RHEL_VER	8	build-arg	N/A	N/A	nothing to do	Base OS version. Debian replaces Rocky Linux.
IMAGE_FROM	rockylinux:8	build-arg	debian:12	N/A	nothing to do	The base image changes from Rocky Linux to Debian 12 (Bookworm). Debian 12 is a stable and supported release.
PHP_VER	7.4	build-arg (rockyLinuxRepo for enable module via Remi)	8.2	main	needs check if php is supported by all packages	Dockerfile explicitly enables PHP 7.4 via Remi's repo. Debian 12 ships with PHP 8.2. Compatibility testing for FreePBX is crucial. May require manual build or third-party repositories for PHP 7.4 on Debian if 8.2 is incompatible.
ASTERISK_VER	20.12.0	downloaded (from GitHub)	20.2.1~dfsg-3	main	outdated, we require to download it by script and upgrade to latest minor update 20.14.1	Asterisk 20.12.0 is a specific release; Debian 12 has 20.2.1. A custom build from source on Debian will likely be needed to match your exact version and configurations.
FREEPBX_VER	16	downloaded (from mirror.freepbx.org and GitHub)	N/A	N/A	nothing to change	FreePBX is not typically in official Linux distribution repositories. It's manually downloaded. The process on Debian would be similar, but dependency versions (PHP, MariaDB) will differ.
FOP2_VER	2.31.45	build-arg	N/A	N/A	outdated, we require to download it by script and upgrade to latest minor update 2.31.47	FOP2 is a commercial module for FreePBX and is not typically found in distribution repositories. Manual installation on Debian.
SPANDSP_VER	3.0.0-6ec23e5a7e	downloaded (from buildroot.net)	0.0.6~pre21-2	main		Spandsp is compiled from source in Dockerfile. Debian has an older version in main. Likely need to recompile from source for the specific version.
IKSEMEL_VER	1.5.1.3	downloaded (from GitHub)	1.6-4.1	main	trying to use debian	Compiled from source in Dockerfile. Debian 12 has a newer version in main. Re-evaluation of custom build or repo version needed.
XMLSTARLET_VER	1.6.1	downloaded (from SourceForge)	1.6.1-3	main	use debian	Compiled from source in Dockerfile. Debian 12 has the same version. Using the repo version might be easier.
BCG729_VER	1.1.1	downloaded (from GitHub)	1.0.2-1	contrib	nothing to change	Compiled from source in Dockerfile. Debian has an older version in contrib. Likely need to recompile from source.
ASTERISK_G72X_VER	master	downloaded (from GitHub)	N/A	N/A	nothing to change	Compiled from source in Dockerfile. This is typically a third-party codec for Asterisk, often built from source.
ASTERISK_CHAN_DONGLE_VER	master	downloaded (from GitHub)	N/A	N/A	nothing to change	Compiled from source in Dockerfile. This is a specific Asterisk channel driver, often built from source.
IZSYNTH_VER	5.0	downloaded (from GitHub)	N/A	N/A	nothing to change	Custom tool from ugoviti's GitHub. Manual installation.
ZABBIX_VER	7.0	build-arg (rockyLinuxRepo for zabbix-release)	6.0.20+dfsg-1	main	nothing to change	Dockerfile uses Zabbix 7.0 (from Zabbix repo). Debian 12 officially provides Zabbix 6.0 LTS in main. Using Debian's repo version is recommended, but 7.0 would require Zabbix's official repositories for Debian.
ZABBIX_TEMPLATE_VER	main	downloaded (from GitHub)	N/A	N/A	nothing to change	Custom Zabbix templates from ugoviti's GitHub. Manual installation.
SNGREP_VER	1.8.2	downloaded (from GitHub)	1.8.2-1	main	trying to use debian	Compiled from source in Dockerfile. Debian 12 has the same version. Using the repo version might be easier.
phpMyAdmin	5.1.4	rockyLinuxRepo (remi-release)	5.2.1+dfsg-1	main	trying to use debian	Installed via remi-release on Rocky. Debian 12 has it in main.
MariaDB	10.5.x	rockyLinuxRepo	10.11.8-1	main	trying to use debian	Rocky Linux 8 typically provides MariaDB 10.5. Debian 12 provides 10.11. Major version difference requires careful migration and testing.
FFmpeg	4.4.x	rockyLinuxRepo (rpmfusion-free-updates)	7:5.6.1+dfsg-1	main	trying to use debian	Installed via rpmfusion on Rocky. Debian 12 has 5.6.1 in main (though newer versions may be in non-free or backports).
ionCube Loader	N/A	downloaded (from ioncube.com)	N/A	N/A	nothing to change	Proprietary PHP extension. Must be downloaded specifically for PHP 8.2 and Debian 12's architecture.
rsync	3.1.3	rockyLinuxRepo	3.2.7-1	main	trying to use debian	Standard package.
net-tools	2.0-0.25.20180220git.el8	rockyLinuxRepo	2.10-1	main	trying to use debian	Standard package.
procps-ng	3.3.15	rockyLinuxRepo	2:4.0.2-3	main	trying to use debian	Standard package.
iptables	1.8.4	rockyLinuxRepo	1.8.9-1	main	trying to use debian	Standard package.
libnetfilter_conntrack	1.0.8	rockyLinuxRepo	1.0.9-1	main	trying to use debian	Standard package.
libnfnetlink	1.2.0	rockyLinuxRepo	1.2.0-1	main	trying to use debian	Standard package.
conntrack-tools	1.4.5	rockyLinuxRepo	1:1.4.6-2.1	main	trying to use debian	Standard package.
libnetfilter_cthelper	1.0.0	rockyLinuxRepo	1.0.0-3	main	trying to use debian	Standard package.
libnetfilter_cttimeout	1.0.0	rockyLinuxRepo	1.0.0-4	main	trying to use debian	Standard package.
libnetfilter_queue	1.0.4	rockyLinuxRepo	1.0.5-2	main	trying to use debian	Standard package.
iftop	1.0~pre4-4	rockyLinuxRepo	1.0~pre4-6	main	trying to use debian	Standard package.
lsof	4.91	rockyLinuxRepo	4.95.0-1	main	trying to use debian	Standard package.
strace	5.7	rockyLinuxRepo	6.1-1	main	trying to use debian	Standard package.
tcpdump	4.9.3	rockyLinuxRepo	4.99.1-1	main	trying to use debian	Standard package.
supervisor	4.2.1	rockyLinuxRepo	4.2.5-1	main	trying to use debian	Standard package.
curl	7.61.1	rockyLinuxRepo	7.87.0-12	main	trying to use debian	Standard package.
opus	1.3.1	rockyLinuxRepo	1.3-1	main	trying to use debian	Standard package.
logrotate	3.14.0	rockyLinuxRepo	3.21.0-1	main	trying to use debian	Standard package.
fail2ban-server	0.11.1	rockyLinuxRepo	1.0.2-2	main	trying to use debian	Standard package.
fail2ban-mail	0.11.1	rockyLinuxRepo	1.0.2-2	main	trying to use debian	Standard package.
fail2ban-sendmail	0.11.1	rockyLinuxRepo	1.0.2-2	main	trying to use debian	Standard package.
libedit	20170329-1	rockyLinuxRepo	3.1-20221030-2	main	trying to use debian	Standard package.
unixODBC	2.3.7	rockyLinuxRepo	2.3.11-1	main	trying to use debian	Standard package.
sox	14.4.2	rockyLinuxRepo	14.4.2+git20190427-3	main	trying to use debian	Standard package.
libxml2	2.9.7	rockyLinuxRepo	2.9.14+dfsg-1	main	trying to use debian	Standard package.
openssl	1.1.1	rockyLinuxRepo	3.0.11-1	main	trying to use debian	Standard package.
newt	0.52.20	rockyLinuxRepo	0.52.23-4	main	trying to use debian	Standard package.
sqlite	3.26.0	rockyLinuxRepo	3.40.1-1	main	trying to use debian	Standard package.
libuuid	2.32.1	rockyLinuxRepo	2.38.1-5	main	trying to use debian	Part of util-linux in Debian.
jansson	2.12	rockyLinuxRepo	2.14-1	main	trying to use debian	Standard package.
binutils	2.30	rockyLinuxRepo	2.40-2	main	trying to use debian	Standard package.
libtool	2.4.6	rockyLinuxRepo	2.4.7-6	main	trying to use debian	Standard package.
ncurses	6.1	rockyLinuxRepo	6.4-4	main	trying to use debian	Standard package.
libtiff	4.0.9	rockyLinuxRepo	4.5.0-3	main	trying to use debian	Standard package.
libjpeg-turbo	2.0.90	rockyLinuxRepo	2.1.5-1	main	trying to use debian	Standard package.
audiofile	0.3.6	rockyLinuxRepo	0.3.6-6	main	trying to use debian	Standard package.
uuid	2.32.1	rockyLinuxRepo	2.38.1-5	main	trying to use debian	Part of util-linux in Debian.
libtool-ltdl	2.4.6	rockyLinuxRepo	2.4.7-6	main	trying to use debian	Standard package.
libsndfile	1.0.28	rockyLinuxRepo	1.2.0-1	main	trying to use debian	Standard package.
wget	1.19.5	rockyLinuxRepo	1.21.3-1	main	trying to use debian	Standard package.
bzip2	1.0.6	rockyLinuxRepo	1.0.8-5	main	trying to use debian	Standard package.
file	5.39	rockyLinuxRepo	1:5.44-3	main	trying to use debian	Standard package.
ilbc	2.0.2	rockyLinuxRepo	2.0.2-1	main	trying to use debian	Standard package.
mariadb-connector-odbc	3.1.6	rockyLinuxRepo	3.1.18-1	main	trying to use debian	Standard package.
mpg123	1.25.10	rockyLinuxRepo	1.31.2-1	main	trying to use debian	Standard package.
nodejs	1:16.20.0	rockyLinuxRepo	18.19.1+dfsg-2	main	trying to use debian	Rocky 8 AppStream provides Node.js 16.x. Debian 12 ships with Node.js 18.x. Major version difference.
libtiff-tools	4.0.9	rockyLinuxRepo	4.5.0-3	main	trying to use debian	Standard package.
cronie	1.5.7	rockyLinuxRepo	3.0pl1-171	main	trying to use debian	Debian uses cron (or cronie package providing cron).
httpd	2.4.37	rockyLinuxRepo	2.4.57-2	main	trying to use debian	Debian uses apache2.
mod_ssl	2.4.37	rockyLinuxRepo	2.4.57-2	main	trying to use debian	Debian uses libapache2-mod-ssl or a2enmod ssl.
php-mysqlnd	7.4.x	rockyLinuxRepo	8.2.7-1	main	trying to use debian	Debian equivalent is php-mysql.
php-process	7.4.x	rockyLinuxRepo	8.2.7-1	main	trying to use debian	Debian equivalent is php-fpm or specific PHP extensions like php-cli.
php-pear	1.10.9	rockyLinuxRepo	1.10.13+submodules+notgz-7	main	trying to use debian	Standard package.
php-mbstring	7.4.x	rockyLinuxRepo	8.2.7-1	main	trying to use debian	Standard package.
php-xml	7.4.x	rockyLinuxRepo	8.2.7-1	main	trying to use debian	Standard package.
php-json	7.4.x	rockyLinuxRepo	8.2.7-1	main	trying to use debian	Standard package.
php-gd	7.4.x	rockyLinuxRepo	8.2.7-1	main	trying to use debian	Standard package.
php-curl	7.4.x	rockyLinuxRepo	8.2.7-1	main	trying to use debian	Standard package.
php-ldap	7.4.x	rockyLinuxRepo	8.2.7-1	main	trying to use debian	Standard package.
mariadb	10.5.x	rockyLinuxRepo	10.11.8-1	main	trying to use debian	See MariaDB entry above.
diffutils	3.7	rockyLinuxRepo	3.9-3	main	trying to use debian	Standard package.
unzip	6.0	rockyLinuxRepo	6.0-27	main	trying to use debian	Standard package.
zip	3.0	rockyLinuxRepo	3.0-12	main	trying to use debian	Standard package.
uriparser	0.9.3	rockyLinuxRepo	0.9.7-1	main	trying to use debian	Standard package.
jq	1.6	rockyLinuxRepo	1.6-2.1	main	trying to use debian	Standard package.
speex	1.2.0	rockyLinuxRepo	1.2.0-1	main	trying to use debian	Standard package.
speexdsp	1.2.0	rockyLinuxRepo	1.2.0-1	main	trying to use debian	Standard package.
portaudio	19.6.0	rockyLinuxRepo	19.7.0-1	main	trying to use debian	Standard package.
libsrtp	2.3.0	rockyLinuxRepo	2.5.0-1	main	trying to use debian	Standard package.
unbound-libs	1.13.1	rockyLinuxRepo	1.17.1-2	main	trying to use debian	Standard package.
freetds	1.2.1	rockyLinuxRepo	1.3.11-1	main	trying to use debian	Standard package.
freetds-libs	1.2.1	rockyLinuxRepo	1.3.11-1	main	trying to use debian	Standard package.
libevent	2.1.8	rockyLinuxRepo	2.1.12-stable-5	main	trying to use debian	Standard package.
net-snmp-libs	5.8	rockyLinuxRepo	5.9.3+dfsg-1.1	main	trying to use debian	Standard package.
codec2	0.9.2	rockyLinuxRepo	1.0.6-1	main	trying to use debian	Standard package.
neon	0.30.2	rockyLinuxRepo	0.32.5-1	main	trying to use debian	Standard package.
libproxy	0.4.15	rockyLinuxRepo	0.4.17-1	main	trying to use debian	Standard package.
net-snmp-agent-libs	5.8	rockyLinuxRepo	5.9.3+dfsg-1.1	main	trying to use debian	Standard package.
lm_sensors-libs	3.4.0	rockyLinuxRepo	3.6.0-7	main	trying to use debian	Standard package.
libical	3.0.4	rockyLinuxRepo	3.0.16-1	main	trying to use debian	Standard package.
libical-devel	3.0.4	rockyLinuxRepo	3.0.16-1	main	trying to use debian	Debian equivalent is libical-dev.
icu	60.2	rockyLinuxRepo	72.1-3	main	trying to use debian	Standard package.
gcc-c++	8.5.0	rockyLinuxRepo	4:12.2.0-3	main	trying to use debian	Debian equivalent is build-essential which includes g++.
make	4.2.1	rockyLinuxRepo	4.3-5	main	trying to use debian	Standard package.
libnsl	1.2.0	rockyLinuxRepo	1.2.0-1	main	trying to use debian	Standard package.
which	2.21	rockyLinuxRepo	2.21-1	main	trying to use debian	Standard package.
fftw-libs	3.3.8	rockyLinuxRepo	3.3.10-2	main	trying to use debian	Standard package.
sudo	1.8.29	rockyLinuxRepo	1.9.13p3-1	main	trying to use debian	Standard package.
figlet	2.2.5	rockyLinuxRepo	2.2.5-3	main	trying to use debian	Standard package.
nc	1.187	rockyLinuxRepo	1.217-1	main	trying to use debian	Debian typically uses netcat-traditional or netcat-openbsd.
dnsmasq	2.84	rockyLinuxRepo	2.89-1	main	trying to use debian	Standard package.
glibc-langpack-en	2.28	rockyLinuxRepo	2.36-9	main	trying to use debian	Debian equivalent is locales and language-pack-en.
perl-DBI	1.641	rockyLinuxRepo	1.643-2	main	trying to use debian	Standard package.
perl-DBD-mysql	4.046	rockyLinuxRepo	4.050-4	main	trying to use debian	Standard package.
cyrus-sasl-plain	2.1.27	rockyLinuxRepo	2.1.28+dfsg-11	main	trying to use debian	Standard package.
cyrus-sasl-md5	2.1.27	rockyLinuxRepo	2.1.28+dfsg-11	main	trying to use debian	Standard package.
libresample	0.1.3	rockyLinuxRepo	0.1.3-7	main	trying to use debian	Standard package.
chrony	4.0	rockyLinuxRepo	4.3-1	main	trying to use debian	Standard package.
postfix	3.5.8	rockyLinuxRepo	3.7.2-2	main	trying to use debian	Standard package.
libuv	1.44.2	rockyLinuxRepo	1.44.2-1	main	trying to use debian	Standard package.
patch	2.7.6	rockyLinuxRepo	2.7.6-3	main	trying to use debian	Standard package.
iproute	5.18.0	rockyLinuxRepo	6.1.0-1	main	trying to use debian	Debian package name is iproute2.
bc	1.07.1	rockyLinuxRepo	1.07.1-3	main	trying to use debian	Standard package.
chkconfig	1.13.1	rockyLinuxRepo	1.13.1-1	main	trying to use debian	Debian uses systemctl enable for service management.
libpcap	1.10.0	rockyLinuxRepo	1.10.1-2	main	trying to use debian	Standard package.
gmime	2.6.20	rockyLinuxRepo	3.0.7-1	main	trying to use debian	Standard package.
msmtp	1.8.8	rockyLinuxRepo	1.8.18-1	main	trying to use debian	Standard package.
mtr	0.94	rockyLinuxRepo	0.95-1	main	trying to use debian	Standard package.
vim-enhanced	8.2	rockyLinuxRepo	2:9.0.1378-2	main	trying to use debian	Debian package is vim.
lame-libs	3.100	rockyLinuxRepo (external RPM)	3.100-3	main	trying to use debian	Installed via external RPM on Rocky. Debian 12 has libmp3lame0.
dmidecode	3.3	rockyLinuxRepo	3.4-1	main	trying to use debian	Standard package.
autoconf	2.69	rockyLinuxRepo	2.71-4	main	trying to use debian	Standard package.
automake	1.16.1	rockyLinuxRepo	1.16.5-1.1	main	trying to use debian	Standard package.
ncurses-devel	6.1	rockyLinuxRepo	6.4-4	main	trying to use debian	Debian equivalent is libncurses-dev.
libxml2-devel	2.9.7	rockyLinuxRepo	2.9.14+dfsg-1	main	trying to use debian	Debian equivalent is libxml2-dev.
openssl-devel	1.1.1	rockyLinuxRepo	3.0.11-1	main	trying to use debian	Debian equivalent is libssl-dev.
newt-devel	0.52.20	rockyLinuxRepo	0.52.23-4	main	trying to use debian	Debian equivalent is libnewt-dev.
kernel-devel	N/A	rockyLinuxRepo	N/A	N/A	do not install at all	Debian equivalent is linux-headers-$(uname -r). This is highly specific to the kernel version and will differ for Debian.
sqlite-devel	3.26.0	rockyLinuxRepo	3.40.1-1	main	trying to use debian	Debian equivalent is libsqlite3-dev.
libuuid-devel	2.32.1	rockyLinuxRepo	2.38.1-5	main	trying to use debian	Debian equivalent is uuid-dev.
jansson-devel	2.12	rockyLinuxRepo	2.14-1	main	trying to use debian	Debian equivalent is libjansson-dev.
binutils-devel	2.30	rockyLinuxRepo	2.40-2	main	trying to use debian	Debian equivalent is binutils-dev.
libedit-devel	20170329-1	rockyLinuxRepo	3.1-20221030-2	main	trying to use debian	Debian equivalent is libedit-dev.
svn	1.14.1	rockyLinuxRepo	1.14.2-2	main	trying to use debian	Standard package.
opus-devel	1.3.1	rockyLinuxRepo	1.3-1	main	trying to use debian	Debian equivalent is libopus-dev.
opusfile-devel	0.12	rockyLinuxRepo	0.12-3	main	trying to use debian	Debian equivalent is libopusfile-dev.
unixODBC-devel	2.3.7	rockyLinuxRepo	2.3.11-1	main	trying to use debian	Debian equivalent is unixodbc-dev.
libtiff-devel	4.0.9	rockyLinuxRepo	4.5.0-3	main	trying to use debian	Debian equivalent is libtiff-dev.
libjpeg-turbo-devel	2.0.90	rockyLinuxRepo	2.1.5-1	main	trying to use debian	Debian equivalent is libjpeg-dev.
audiofile-devel	0.3.6	rockyLinuxRepo	0.3.6-6	main	trying to use debian	Debian equivalent is libaudiofile-dev.
uuid-devel	2.32.1	rockyLinuxRepo	2.38.1-5	main	trying to use debian	Debian equivalent is uuid-dev.
libtool-ltdl-devel	2.4.6	rockyLinuxRepo	2.4.7-6	main	trying to use debian	Debian equivalent is libltdl-dev.
libsamplerate-devel	0.1.9	rockyLinuxRepo	0.1.9-4	main	trying to use debian	Debian equivalent is libsamplerate0-dev.
libsndfile-devel	1.0.28	rockyLinuxRepo	1.2.0-1	main	trying to use debian	Debian equivalent is libsndfile1-dev.
doxygen	1.8.14	rockyLinuxRepo	1.9.5-2	main	trying to use debian	Standard package.
bison	3.0.4	rockyLinuxRepo	2:3.8.2+dfsg-1	main	trying to use debian	Standard package.
fftw-devel	3.3.8	rockyLinuxRepo	3.3.10-2	main	trying to use debian	Debian equivalent is libfftw3-dev.
flex	2.6.4	rockyLinuxRepo	2.6.4-8	main	trying to use debian	Standard package.
graphviz	2.40.1	rockyLinuxRepo	2.42.2-6	main	trying to use debian	Standard package.
libpq-devel	13.4	rockyLinuxRepo	15.6-0+deb12u1	main	trying to use debian	Debian equivalent is libpq-dev.
libxslt-devel	1.1.33	rockyLinuxRepo	1.1.37-2	main	trying to use debian	Debian equivalent is libxslt1-dev.
net-snmp-devel	5.8	rockyLinuxRepo	5.9.3+dfsg-1.1	main	trying to use debian	Debian equivalent is libsnmp-dev.
libcurl-devel	7.61.1	rockyLinuxRepo	7.87.0-12	main	trying to use debian	Debian equivalent is libcurl4-openssl-dev.
openldap-devel	2.4.46	rockyLinuxRepo	2.5.13+dfsg-5	main	trying to use debian	Debian equivalent is libldap2-dev.
popt-devel	1.16	rockyLinuxRepo	1.19-1	main	trying to use debian	Debian equivalent is libpopt-dev.
bluez-libs-devel	5.56	rockyLinuxRepo	5.66-1	main	trying to use debian	Debian equivalent is libbluetooth-dev.
gsm-devel	1.0.17	rockyLinuxRepo	1.0.18-1	main	trying to use debian	Debian equivalent is libgsm-dev.
libsrtp-devel	2.3.0	rockyLinuxRepo	2.5.0-1	main	trying to use debian	Debian equivalent is libsrtp2-dev.
libvorbis-devel	1.3.6	rockyLinuxRepo	1.3.7-1	main	trying to use debian	Debian equivalent is libvorbis-dev.
lua-devel	5.3.5	rockyLinuxRepo	5.3.6-2	main	trying to use debian	Debian equivalent is liblua5.3-dev (note: Debian 12 has Lua 5.3).
neon-devel	0.30.2	rockyLinuxRepo	0.32.5-1	main	trying to use debian	Debian equivalent is libneon27-dev.
speex-devel	1.2.0	rockyLinuxRepo	1.2.0-1	main	trying to use debian	Debian equivalent is libspeex-dev.
speexdsp-devel	1.2.0	rockyLinuxRepo	1.2.0-1	main	trying to use debian	Standard package.
codec2-devel	0.9.2	rockyLinuxRepo	1.0.6-1	main	trying to use debian	Debian equivalent is libcodec2-dev.
freetds-devel	1.2.1	rockyLinuxRepo	1.3.11-1	main	trying to use debian	Debian equivalent is freetds-dev.
portaudio-devel	19.6.0	rockyLinuxRepo	19.7.0-1	main	trying to use debian	Debian equivalent is libportaudio2-dev.
radcli-devel	1.2.10	rockyLinuxRepo	1.2.12-1	main	trying to use debian	Debian equivalent is libradcli-dev.
uriparser-devel	0.9.3	rockyLinuxRepo	0.9.7-1	main	trying to use debian	Debian equivalent is liburiparser-dev.
uw-imap-devel	2007f	rockyLinuxRepo	2007f~dfsg-8	main	trying to use debian	Debian equivalent is uw-imap-dev or related PHP IMAP packages. Often not directly needed for web applications on modern setups.
sox-devel	14.4.2	rockyLinuxRepo	14.4.2+git20190427-3	main	trying to use debian	Debian equivalent is libsox-dev.
ilbc-devel	2.0.2	rockyLinuxRepo	2.0.2-1	main	trying to use debian	Debian equivalent is libilbc-dev.
python3-devel	3.6.8	rockyLinuxRepo	3.11.2-1	main	trying to use debian	Debian equivalent is python3-dev. Note the significant version difference in Python 3.
cmake	3.20.2	rockyLinuxRepo	3.25.1-1	main	trying to use debian	Standard package.
libresample-devel	0.1.3	rockyLinuxRepo	0.1.3-7	main	trying to use debian	Debian equivalent is libresample-dev.
mariadb-devel	10.5.x	rockyLinuxRepo	10.11.8-1	main	trying to use debian	Debian equivalent is libmariadb-dev.
libuv-devel	1.44.2	rockyLinuxRepo	1.44.2-1	main	trying to use debian	Debian equivalent is libuv1-dev.
xmlto	0.0.28	rockyLinuxRepo	0.0.28-4.2	main	trying to use debian	Standard package.
docbook5-schemas	5.0	rockyLinuxRepo	5.0-6	main	trying to use debian	Standard package.
gmime-devel	2.6.20	rockyLinuxRepo	3.0.7-1	main	trying to use debian	Debian equivalent is libgmime-3.0-dev.
jack-audio-connection-kit-devel	1.9.12	rockyLinuxRepo	1.9.22~dfsg-2	main	trying to use debian	Debian equivalent is libjack-jackd2-dev.
libcap-devel	2.48	rockyLinuxRepo	1:2.66-3	main	trying to use debian	Debian equivalent is libcap-dev.
libpcap-devel	1.10.0	rockyLinuxRepo	1.10.1-2	main	trying to use debian	Debian equivalent is libpcap-dev.
rpm-devel	4.14.3	rockyLinuxRepo	N/A	N/A	do not install at all	Debian uses .deb packages; rpm-devel is specific to RPM-based systems. Not directly applicable for Debian builds.
mariadb-connector-c-devel	3.1.11	rockyLinuxRepo	3.1.18-1	main	trying to use debian	Debian equivalent is libmariadbclient-dev.
libogg-devel	1.3.3	rockyLinuxRepo	1.3.5-0+deb12u1	main	trying to use debian	Debian equivalent is libogg-dev.
cmake-data	3.20.2	rockyLinuxRepo	3.25.1-1	main	trying to use debian	Standard package.
libmodman	2.0.1	rockyLinuxRepo	N/A (deprecated in el9)	N/A	do not install at all	Deprecated in RHEL 9. May or may not be directly available/needed in Debian.
pakchois	0.4	rockyLinuxRepo	N/A (deprecated in el9)	N/A	do not install at all	Deprecated in RHEL 9. May or may not be directly available/needed in Debian.
incron	0.5.10	rockyLinuxRepo	0.5.13-1	main	trying to use debian	Deprecated in RHEL 9, but available in Debian 12.
python2	2.7.18	rockyLinuxRepo	N/A	N/A	do not install at all	Python 2 is End-of-Life and is not available in Debian 12's main repositories. If absolutely needed, alternative installation methods would be required, but strong recommendation to upgrade to Python 3.
libtermcap-devel	N/A	rockyLinuxRepo	N/A	N/A	do not install at all	Debian usually handles this via libncurses-dev. Not a standalone package in Rocky 8 usually, nor directly in Debian.
unbound-devel	1.13.1	rockyLinuxRepo	1.17.1-2	main	trying to use debian	Debian equivalent is libunbound-dev.
	the exact version might vary slightly depending on minor updates within the Debian Bookworm release cycle or if you're using backports.